## Proj plan
BLOGGER MANAGE SYSTEM
# | Task | Duration (days) | Start Date | End Date | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Planning, Requirement Analysis & design architecture | 0.5 | 2022-07-07 | 2022-07-07
2 | Development/ Implementation of the System | 2 | 2022-07-08 | 2022-07-09
3 | Testing & bug fixing | 1 | 2022-07-10 | 2022-07-10
4 | Documentation | 0.5 | 2022-07-11 | 2022-07-11